# ECLIPSE –

# Essential Climate Logging, Integration & Processing for Space Environments

Project Plan- Light grey rows are completed.

| Stage | Task | Deadline | Notes |
| --- | --- | --- | --- |
| October | Research + system design + setup |  |  |
| Foundation & Setup | -Finalise project scope and objectives for ECLIPSE. -Research candidate sensors (temperature, humidity, CO₂, radiation, pressure). | 05/10/25 | ESP32 circuit board, BME680, SCD30, SEN-0168, Qwicc Cables [Need to order, short delivery times] |
| Foundation & Setup | -Define system requirements -Draw system architecture (sensor → board → logging → database → dashboard) | 12/10/25 | Similar to analysis and design documents |
| Foundation & Setup | -Setup development environment (C++ toolchain, SQLite, GitHub repo). -Experiment with one sensor or simulator → write a basic program to capture readings. | 19/10/25 | Set up on hard drive, avoid space issues. |
| Foundation & Setup | -Draft project proposal/report intro + methodology. -Deliverable: small proof-of-concept — log one variable (e.g., temperature) into SQLite. | 25/10/25 | Shouldn’t take too long to do this! |
| November | Build robust logging system |  |  |
| (Core Logging & Data Handling) | -Implement multi-sensor logging -Define CSV + SQLite schema (timestamp, sensor type, value). -define a single flexible readings table (ISO-8601 UTC timestamps, metric, value, unit, sensor_id, quality, meta) | 9/11/25 | Just add all types of sensors readings. |
| (Core Logging & Data Handling) | -Write module for continuous data acquisition (loop + error handling). -Add basic thresholds (e.g., alert if CO₂ > X ppm). | 16/11/25 | Just add stubs for alerts, will be implementing next month |
| (Core Logging & Data Handling) | -Build dashboard prototype (CLI or minimal GUI). -Display live values + recent logs. | 23/11/25 | Use Figma for prototyping, (Lots of research on UX) |
| (Core Logging & Data Handling) | - Integrate all components (sensors → DB → UI). -Mid-point evaluation: reliability check, fix bugs. | 30/11/25 | (Difficult week, consult for help) |
| December | Build alerts system using logging & console warnings |  |  |
| (Processing & Alerts) | - Implement data processing module (averages, min/max, rolling windows). & plan outlier filtering. -Add visualisation for trends (graph or table). | 07/12/25 | Cmath module would be great for this. Research for graphical displays. |
| (Processing & Alerts) | Implement alerting system (console warnings, log flags, or simple notifications). | 14/12/25 | System will include dwell times [how long a breach lasts before alert] and severity bands: [caution/warning/critical] |
| (Processing & Alerts) | Combine processing + alerts (e.g., high CO₂ triggers red warning in UI). | 21/12/25 | Doesn’t have to be red specifically. |
| (Processing & Alerts) | -Documentation catch-up (system design, methodology). -Deliverable: working prototype logging multiple variables + alerts. | 31/12/25 | Slow week for Christmas. Just writing for project |
| January | Strengthen and expand system |  |  |
| (Advanced Features & Integration) | -Add mission environment simulation (e.g., simulate space capsule conditions). -scenario file (24h day, with 2 off-nominal events) | 11/01/26 | Busy week, try look into different environments, space, earth etc. Look at how the system will differ in these events. Simulation is also a must and is time consuming!!! |
| (Advanced Features & Integration | -Add more advanced processing (correlation between variables, anomaly detection). | 18/01/26 | Anomaly detection is a must & calibration log? |
| (Advanced Features & Integration) | Refine dashboard UI (modular views, better data presentation). | 25/01/26 | A slow week, for refining. |
| (Advanced Features & Integration) | Run end-to-end demo with all modules (logging, storage, alerts, UI). | 31/01/26 |  |
| February | (Testing & Evaluation) |  |  |
| (Testing & Evaluation) | Unit tests for sensor logging, DB insertions, processing. | 07/02/26 | Latency testing!!!!! Needs to be added |
| (Testing & Evaluation) | Stress test system with simulated high-frequency data. | 14/02/26 |  |
| (Testing & Evaluation) | Evaluate performance: storage use, response times, error tolerance. | 21/02/26 |  |
| (Testing & Evaluation) | Write Results & Evaluation section. | 28/02/26 |  |
| March | (Polish & Final Write-up) |  |  |
| (Polish & Final Write-up) | Final fixes + ensure UI stability. | 07/03/26 |  |
| (Polish & Final Write-up) | Write final dissertation chapters (discussion, conclusion). | 14/03/26 |  |
| (Polish & Final Write-up) | Full draft complete → proofreading + references. | 21/03/26 |  |
| (Polish & Final Write-up) | Prepare final deliverables (submission files, demo video, poster). | 31/03/26 |  |